## Sheet1
YouMatch CoP 2
Career Guidance and Life Skills
Intervention Area | Proposed Activity | Expected Result | Evaluating Progress | Reponsible | Timeline | [6 empty] | Comments
[5 empty] | Oct | Nov | Dec | Jan | Feb | Mar | Apr
A1: Systematic Integration of Career Guidance (Curricula) in national systems | Presentation/Discussion of current mode of career guidance services delivery in Jordan/ National Strategy Paper | Insight into the national system in Jordan, Peer Feedback to the National Strategy Paper |  | Rabeah, Dina | [7 empty] | tentative date: 26th or 27th November (10:00-12:00 GMT+2) | bar: Timeline Nov; Timeline Jan
| Presentation of CAP YEI Best Model; Contribution of CAP YEI experience to national TVET reform in Kenya | Insight into CAP YEI'S Career Guidance Curricula as well as the national system in Kenya |  | Ndungu | [7 empty] | tentative date: 15th or 16th of January (10:00-12:00 GMT+2) | bar: Timeline Jan
| Presentation on "What employers think of millenials? (employer requirements) | Understanding of private sector perspective on youth |  | Emmanuel | Timeline Jan: date to be discussed | Date will be coordinated with Emmanuel and CoP members in the upcoming weeks
| Study tour to contries with advance programme in CG for skills providers | exchange experiences; exposure to best practices; discussion adaptation to local contexts |  | Dina, Rabeah, Ndungu, Ondieki; YouMatch | [7 empty] | Location and content to be specified after the next online meetings. Dina to help with background research ; GIZ supports with contacts and logistics. Step 1: Development of a criteria which will assist in identifying the appropriate country and institutions to visit. The study tour shall also include an input on A2, e.g. on the certification of CG providers in a national system | bar: Timeline Feb to Timeline Mar
| Online Session: CG Curricula design (systematic view) |  |  | possibly Helmuth Zelloth | Timeline Oct: Date to be discussed | YouMatch will identify expert Emphasis on LS&CG in the informal and formal sector
A2: Career Guidanced providers (Certification) | Online Session: Delivery of Career Guidance in schools; Case Study Germany |  |  | Suggestion: Michaela Henn | Timeline Feb: Date to be discussied | Rabeah may provide more information on this example
A3: Validation/Discussion of already suggested policies | validation of AU CG Framework | validation of the already elaborated framework |  | Ndungu | Timeline Oct: Date to be discussed with AUC representatives | CoPs to bring experiences on stakeholder cooperation. Discussions with AU team will be held during the steering committee meeting, Nov 2019, Bonn.
| discussion of national strategy paper on CG (Jordan) | discussion and peer-review/input on national strategy paper on CG |  | Rabeah | [7 empty] | see above | bar: Timeline Oct to Timeline Nov