## CoP 1 ENG (hidden)
COP 1 - Using Labour Market Information as a basis for effective employment services for youth
Value Proposition
This CoP on using labour market information as an essential basis for effective employment services for Youth aims to support employment service providers both public and private who want to capitalize on their labour market information systems by providing analysis, knowledge, good practice and innovation on labour market information systems which will enable stakeholders to effectively benchmark and develop learning opportunities regarding the effective use of LMIS.
Intervention Area | Poposed Activity | Expected Results | Responsible person(s) | Expected Date | Comments |  |  |  |  | Comments
|  |  |  | Sep | Oct | Nov | Dec | Jan | Feb
Provision of Up to Date Labour Market Information | Define Elements of presenation | Developed Country Presentation | COP Members | [6 empty] | Planning? Possibly to define the elements within the proposed country presentations
Skills Anticipation Linking Supply and demand | Presenation country Situational analysis SWOT | Idenitifed common gaps | Country Profile CoP specific | [6 empty] | 1. Common gaps identified from country presentations to decide further action/activities in strengthening these areas 2. Could be linked to the study tour activity to see how other countries are addressing the known gaps in the countries
Ensure a sustainable Network of Stakeholders to run LMI | Study Tour Korea Germany + Netherlands | Knowledge on best practices | Facilitator and GIZ focal point
Institutional arrangement to use LMI information as a basis for Employment Services | Link to SIFA on Pilot LMIS projects | Additional Activities to be identified | [7 empty] | Follow up will be made with SIFA when the advisor is appointed. Anticipated to begin October 2019

## CdP 1 FR (hidden)
COP 1 - Using Labour Market Information as a basis for effective employment services for youth
Proposition de Valeur
Cette communauté de pratique est composée de membres de divers praticiens des services de l'emploi des secteurs public et privé de divers pays africains. Il a été créé pour surveiller les services d’emploi pour les jeunes et agir pour les jeunes en aidant les acteurs du marché du travail en Afrique à mieux utiliser l’information grâce au développement de services de l’emploi efficaces pour mieux faire face au problème du chômage des jeunes.
|  |  |  | Sep | Oct | Nov | Dec | Jan | Fev | Mar | Avr
Gouvernance d'un SIMT (coordination, alimentation, plaidoyer, Mobilization parties prenante, coherence) | Formation: En Allemagne (Voyage d'Etude). * Cadre Acteurs * Gouvernance | Renforcement des compétences de la CdP en matière de gouvernance et de gestion du SIMT | YouMatch et CdP
Dispositif de prospective sur le MT (veille prospective, Anticipation emploi competence) | WEBINAR: Réaliser un état des lieux dans nos pays respectifs | Bonnes practiques et identifié | CdP
| REUNION EN LIGNE EXPERT INTERN: Examen des pratiques internationales | Bonnes practiques et partagées | YouMatch et CdP
| ECHANGE EN LIGNE: Choisir et définir les dispositif ( méthodologie, choix d'indicateurs, secteurs cibles) | Méthodologie choisie et adaptée , indicat définis | CdP et Expertise externe (Youmatch) | [8 empty] | informe l'activité suivante
| FORMATION: Renforcer les capacités des membres de la CdP1 sur la méthodologie retenue. | Bonnes maitrise par les membres de la CdP de la méthodologie a déployer | Youmatch et Expertise externe
| ECHANGE EN LIGNE: Conception des outils à utiliser pour la collecte d'informations sur le marché du travail (questionnaires, plan d'échantillonnage, spécifications) | Outils et matériels disponible | CdP et Expertise externe
| ECHANGE EN LIGNE: Finaliser et Valider | Matériels validés - Atelier de restitution réalisé | CdP + Youmatch
Système d'information sur la meilleure façon d'adapter les programmes d'emploi actif en leur faveur

## COP (1) Action Plan
JOINT COP 1 ENG/FR ACTION PLAN
BLOCK 1
LMI Governance and Institutional Arrangement
Poposed Activity | Expected Results | Responsible person(s) | Expected Date | Comments |  |  |  |  | Comments
|  |  | Sep | Oct | Nov | Dec | Jan | Feb
Online Meeting To prepare study tour and | Identification of elements and expectations of Study Tour | GIZ TM, Facilitator, Members | Comments Oct: End Week 21-28 Oct; Comments Nov: x
Study Tour on LMI Governance and Institutional arrangement | Deepening of common understanding of LMI and actors | GIZ YM | Comments Dec: 1st Week 2-6 Dec | Proposed countries for Study Tour: Europe (to be defined) African Union Commission may be invite to join Study tour will be done with other language LMI CoP 3 day programme - 2 days site visit - 1 day brainstorming/strategizing
Mapping of LMI approaches in various countries (member countries) Exchange of experience on LMI governance among members | Country presentations and mapping of LMI in each context Strengthen group understanding of LMI in from each member state Exhanges on good Practice | YM members | [6 empty] | Define and develop elements of presentations and mapping exercise, this can be agreed upon and defined during the study tour Experts may be invited to comment on the presentations | bar: Comments Dec to Comments Jan
Webinar exchanges with experts on the topics of LMI governance to highlight a multi dimensional approach. | Expansion of the groups views in the field of LMI | GIZ, ETF, Members | [6 empty] | ETF experts will be made available | bar: Comments Feb
Drafting of Recommendations on LMI Governance | CoP contributes to a new or exisiting Policy document, Recommendation at the regional level | GIZ YM, Members | [6 empty] | The AUC through Mr Oumar Diop would give further direction and orientation.
BLOCK 2
Skills Anticipation (Tools and Methodology)
Poposed Activity | Expected Results | Responsible person(s) | Expected Date Sep: Expected Date; Comments Oct: Comments | Comments
|  |  | Sep | Oct | Nov | Dec | Jan | Feb
Online meeting to exchange experience and best practices | Understanding each members position on Skills anticipation in their respective countries Identification of transferable and replicable best practices from each country | Members
Webinar with external expert to learn about international best practices | Broadening CoPs undertanding of skills anticipation in the international context and possibly identify ways transferable approaches to Skills anticipation | GIZ YM , ETF
Exchange face to face / series of webinar (TBD) |  | GIZ YM | [6 empty] | This study tour, face to face activity will be more clearly defined through the process of mapping the contexts of Skill Anticipation in each member state and through the provision of international best practices.
Drafting of policy recommendations on skills anticipation |  | Members
AUC and AUDA COP Participation / Transversal
Poposed Activity | Expected Results | Responsible person(s) | Expected Date Sep: Expected Date; Comments Oct: Comments | Comments
|  |  | Sep | Oct | Nov | Dec | Jan | Feb
Online Exchange with AUC to give direction on work and recommendations | Clear outline on Joint Product (policy recommendation) that the CoPs will be asked to contribute to, or develop. | GIZ YM, AUC | [6 empty] | This is to allow the AUC to give orientation to the groups aspects of learning and make provisions for to contribute to the 2016 LMI proposal
Online Exchange with ILO on LMI (within the framework of SIFA implementation) | Identify synergies of ILO and SIFA proposed activities CoP members can participate in. | GIZ YM | [6 empty] | ILO and SIFA plan to implement LMI in a number of countries. As well as the implementation, further capacity development measures will be undertaken. CoP members may be able to participate in these capacity development measures in line with the ILO and SIFA plan of action. The SIFA focus on this regard is strongly on LMI and its institutional arrangement and involves eements of peer learning and mapping excercises