## Sheet1
YOUMATCH MSD 4 YES DRAFT PLAN OF ACTION (October 2019 - April 2020)
Multi Stakeholder Dialogue for Youth Employment Services
Intervention Area | Proposed Activity | Expected Result | Evaluating Progress | Reponsible | Timeline | [6 empty] | Comments
[5 empty] | October | November | December | January | February | March | April
A1: Research and Information Seeking | A1.1: Collect information country level, develop tools, surveys, focus group and online research | Share a status report for each country represented in the COP |  | Lawrence | [7 empty] | Identify tools for collecting information of who and where. Technical support needed. | bar: Timeline October to Timeline December
| A1.2. Collect international best practices | Share status report on international best practices |  | Opio, Amal, Diana, Benjamin | [7 empty] | Identify countries for best practices case studies. Technical support needed | bar: Timeline October to Timeline December
| A1.3. Benchmarking best practices- STUDY TOUR | Study tour on best practice for benchamarking |  | David, Zain, Valence | [7 empty] | Identify countries for best practices case studies. Technical support needed | bar: Timeline February to Timeline March
| A1.4. Data analysis and recommendation | Recommendation for model development |  | Sewit, Gidado, Emmanuel | [7 empty] | Technical support needed | bar: Timeline March to Timeline April