## Slide 1
Draft joint action plan: CdP1 / CoP1
January 2020 – May 2021
Following the Study Tour on “ Labour Market Information” 02 - 06 December 2019
North Rhine-Westphalia, Germany

## Slide 2
Action 1: LMIS governance
Objective: to elaborate and promote an LMIS governance model for Africa

## Slide 3
To set up a Working Group (comprising voluntary members from CdP1/CoP1) that will draft a model / guidelines on LMIS governance (in part based on the holistic Rwandan example)
To ensure coordination between the WG and the CdP / CoP through regular exchanges on Go To Meeting and comment rounds
Opportunity for CoP / CdP members to present their own national model via Go To Meeting (so that WG could pick best practices and integrate in model / guidelines: e.g. stakeholder mappings, value chains, MoUs, terms of reference, standardization of LMI reports/indicators, legal framework to impose LMI sharing)
To secure coordination of the WG with AUC during the elaboration of the model / guidelines
Opportunity to exchange via webinars with ETF experts if required
Finalization and validation of the model / guidelines by the CdP / CoP members
Step 1: drafting of a governance model / guidelines on LMIS for Africa
1
2
3
4
5
6

## Slide 4
To set up a Working Group (comprising voluntary members from CdP1/CoP1) that will elaborate an action plan to promote the model
WG / AUC to identify opportunities to promote the model in collaboration with AUC (e.g. AU STC meetings, PAP Sessions, Africa Creates Jobs conference)
WG to prepare and run side events / workshops at targeted conferences in collaboration with AUC (incl. AU STC meetings, PAP Sessions,, Africa Creates Jobs mid-2020)
Step 2: promotion of the model /guidelines on LMIS for Africa
1
2
3

## Slide 5
Action 2: Exchange of best practices on LMI
Objective: to exchange best practice / expertise on surveys and anticipation tools amongst CdP/CoP members

## Slide 6
Series of online meetings to exchange experiences amongst interested members on information collection tools and methods (e.g. enterprise panel surveys, methods to collect information on informal sector), decision support instruments and target-group adapted dissemination methods
Opportunity to exchange via webinars with ILO experts e.g. on skills anticipation tools if required
Agreement within the CoP / CdP on a list of national experiences to be shared / presented within the CoP / CdP
1
2
3